## Editry_Shield_90_Day_Launch_Pla
Project | Person | Status | Date | Definition of Done
Finalize operating agreement under The Editry Collective | Ashley |  | 2025-11-08 | Signed and stored in company drive
Conduct call with Aleks (security firm owner) | All / Marlon lead |  | 2025-11-04 | Debrief summary & checklist created
Identify GA licensing requirements (company, manager, armed/unarmed guard) | Marlon |  | 2025-11-10 | Documented steps, forms, and fees
Build 20-line grant pipeline spreadsheet (veteran/minority/small-biz grants) | Marlon |  | 2025-11-15 | Spreadsheet completed with Name, Link, Deadline, Amount
Register Editry Shield DBA / subsidiary filing (if required) | Ashley |  | 2025-11-18 | Confirmation of registration under EIN
Obtain initial business insurance quotes (GL, workers’ comp, auto) | Marlon |  | 2025-11-22 | 3 comparable quotes documented
Define budget categories and create startup budget sheet | Paris + Ashley |  | 2025-11-25 | Budget baseline reviewed & approved
Select accountant/bookkeeper for startup support | Ashley |  | 2025-11-27 | Confirmed resource or platform (Gusto/QuickBooks/etc.)
Finalize logo lockup & color palette (Editry Shield visual identity) | Paris |  | 2025-12-02 | Approved vector assets uploaded
Develop landing page (/shield) with service overview & CTA | Paris + Ashley |  | 2025-12-09 | Page live, tested on desktop + mobile
Create social media accounts (LinkedIn, Instagram, Facebook) | Paris |  | 2025-12-09 | Profiles branded, bios aligned
Write & publish Shield intro post + soft-launch announcement | Paris |  | 2025-12-12 | Live across all channels
Build one-pager + rate card + digital brochure | Paris |  | 2025-12-16 | Shareable PDF assets complete
Configure HubSpot pipeline for Shield leads | Ashley |  | 2025-12-18 | Lead form active, routing tested
Shortlist and demo 2–3 guard management software options | Marlon |  | 2025-12-20 | Decision memo with recommendation
Secure first partnership or referral contact | Marlon |  | 2025-12-23 | One qualified lead or referral call booked
Submit all GA security licensing applications | Marlon |  | 2026-01-03 | Confirmation of submission
Purchase insurance + surety bond (pending license approval) | Ashley |  | 2026-01-06 | Certificates on file
Secure minimal office lease or shared workspace | Ashley |  | 2026-01-10 | Signed lease or workspace agreement
Procure uniforms + ID badges (final branding) | Marlon |  | 2026-01-15 | Vendor selected, samples ordered
Launch internal ops handbook (SOPs for scheduling, payroll, incident reporting) | Ashley |  | 2026-01-20 | SOP doc version 1 published
Conduct soft-launch campaign — outreach to 10 prospects via email/social | Paris |  | 2026-01-24 | 10 outreach logs with follow-ups
Apply for at least 3 grants or microloans (SBA, VA, Citi, etc.) | Marlon |  | 2026-01-27 | Submitted with confirmation emails
Review KPIs: cost baseline, leads, grant status, licensing progress | All |  | 2026-01-31 | Summary report + go/no-go for Q2 expansion