## EditryShield_Website_Epics
Epic ID | Epic Title | Purpose / Summary | Key Deliverables | Story Points (Total) | Est. Hours | Dependencies | Definition of Done
1 | Site Framework & Brand Configuration | Establish the HubSpot environment and site foundation with consistent brand identity. | HubSpot access confirmed; Site tree created; Brand colors, fonts, and logo applied; Reusable content modules built. | 8 | 4 | None | Theme configured and pages ready for content loading.
2 | Content Implementation & Page Development | Populate all defined pages with approved copy, formatting, and links. | Home, About, Services Overview, 5 Service Pages, Industries, Careers, Contact. | 16 | 6 | 1 | All pages live, formatted, and linked; copy and CTAs correct.
3 | Consultation Scheduling & Lead Automation | Replace static forms with HubSpot Meeting scheduler and CRM automation. | HubSpot Meeting link embedded site-wide; Confirmation and reminder emails; Auto-created contact and meeting records. | 8 | 3 | 2 | Visitors can book consults; data captured automatically in CRM.
4 | Inter-Page Navigation & Quality Assurance | Ensure site navigation, SEO, and accessibility compliance. | Consistent header/footer nav; Metadata and alt text; Mobile QA checklist. | 9 | 2 | 2 | All links functional; metadata present; passes QA review.
5 | Agile Process Adoption | Establish agile cadence for Editry Shield team operations. | Kanban board setup; Daily stand-ups; Retro at sprint end; Agile terms understood. | 4 | 1 | None | Team uses daily stand-up and retro; progress visible on board.
6 | Analytics & Reporting | Implement visibility into website traffic and lead conversion. | HubSpot tracking; Google Analytics/Search Console; HubSpot dashboard and monthly report template. | 5 | 2 | 4 | Tracking verified; dashboard visible; first report auto-emails.
7 | Legal & Trust Compliance | Add credibility and regulatory baseline. | Privacy Policy, Terms of Service, Licensing info; Trust badges (licensed, insured, veteran-owned). | 3 | 1 | 2 | Footer links active; trust statements visible on site.
8 | Launch Preparation & Post-Go-Live | Structured launch and short hyper-care phase. | Pre-launch checklist; Soft launch; Public announcement; Post-launch retro. | 5 | 2 | 4 | Launch executed; internal sign-off complete; retro held.
9 | Lead Handling & SLA Definition | Define internal process for responding to inbound bookings. | Documented 24-hr SLA; Lead owner assigned; Follow-up email template created. | 4 | 1.5 | 3 | SLA posted; automation and templates functional.
10 | Content Governance & Future Growth | Plan for long-term content maintenance and scalability. | Content Inventory sheet; How-to-update SOP; Future backlog for blog/case studies. | 4 | 1 | None | Governance doc approved; SOP tested by Marlon.