## Slide 1
Proposal Professional Impact Paper
Detroit Public Schools/RNA Recompete Bid Rescue and Reuse
Candidate Name: Timothy Semenza APMP Candidate Number: 28366 Timeframe: November 2025 to January 2026

## Slide 2: Summary of Impact
In 20 working days, I took control of an unprepared $85M Detroit Public Schools recompete, coordinated about 15 stakeholders, reached 2 finalist presentations, and turned the work into reusable RNA school-bid infrastructure.
Category | Evidence
Strategic importance | Incumbent work represented more than 25% of RNA's book of business and expanded from about $14M current scope to an $85M target
Leadership role | I led 100% of coordination and about 60% of drafting across executives, pricing, operations, engineering, account management, and an external consultant
Immediate outcome | Compliant submission completed inside about 20 working days and advanced to 2 finalist presentations
Sustained outcome | Detroit-developed content and templates were reused on about 12 later school bids, including about 6 active at once immediately afterward
A high-risk recompete became a reusable school-bid operating model within one compressed pursuit cycle.

## Slide 3: The Situation
RNA encountered a Detroit Public Schools recompete without a clear capture plan, minimal executive involvement in the RFP, and a late external consultant, despite the incumbent work making up over 25% of its business.
Stakeholder Group | Who Was Involved | Why They Mattered
Senior leaders | Victoria Arinze (CRO) Mufid Farha (CEO) Mohammad Mufid (COO) Brant Miller (EVP, Ops) | Set direction, made decisions, and represented RNA in finalist activity
Core delivery team | Timothy Semenza (Senior Prop. Manager) Chris Arlen (Proposal Consultant) | Coordinated the pursuit and drafted the response
Solution contributors | Ann Couzins (Senior Pricing Manager) Cheryl Holley-Stanton (Account Manager) Finance, operations, IT | Supplied pricing, staffing, operational, and engineering inputs needed for a credible response
Proposal governance had to replace missing capture discipline before the team could compete credibly.

## Slide 4: Stakeholder Engagement and Communication
Direct engagement with senior and additional stakeholders was critical because the organization had limited preparation and I had to lead without formal authority.
Stakeholder Group | How I Engaged Them | Evidence of Leadership
Senior leaders | Frequent working sessions, at peak as much as twice daily, plus live decision and review sessions | I set direction, aligned next actions, and led the live, in-person finalist strategy discussion under pressure
Pricing and solution contributors | Live interviews, pricing and staffing mediation, compliance tracking, and focused review of bid-specific changes | I translated pricing and operational discussion into compliant narrative and kept disputed issues from stalling the bid
Consultant and support team | Shared company context, managed drafting split, and maintained SharePoint submission structure | I remained the single point of coordination while enabling useful support from Chris Arlen
Direct engagement and communication created alignment where authority alone would not.

## Slide 5: Tasks
I stabilized the pursuit through five leadership tasks that gave the team structure, accountability, and decision discipline.
Task | Why It Was Necessary | Main Stakeholders Impacted
Establish bid governance and schedule | No usable capture plan or agreed review cadence existed at release | All senior stakeholders and the external consultant
Develop evaluator and win-theme strategy | The team needed a customer-centered strategy instead of an internally driven narrative | RNA executives, Account Management, and presentation speakers
Elicit and structure SME input | Live operational knowledge had to be turned into compliant proposal content | Pricing, operations, engineering, and Account Management
Draft and quality-control content | The written response and finalist materials had to stay aligned and submission-ready | Consultant, executives, reviewers, and evaluators
Lead review and submission readiness | Readiness could not be left to last-minute judgment | Executive reviewers, consultant, and submission support
Clear task ownership turned a fragmented effort into a manageable response.

## Slide 6: Activities
I used a milestone-led operating cadence to keep the pursuit on track from RFP receipt through two finalist rounds.
Checkpoint | Approx Timing | What Had To Be Complete | How I Controlled It
RFP receipt and planning | Day 1 | Automated schedule, project plan, and working cadence issued | Power Automate schedule logic and immediate visibility of milestones
Kickoff and evaluator strategy | Days 1 to 2 | Leadership aligned on approach, evaluator research framed, responsibilities assigned | Live kickoff plus customer-focused positioning before drafting expanded
Compliance matrix and SME baseline | Days 2 to 5 | Compliance matrix built and core pricing, operations, and account insight captured | Interviews, Teams follow-up, and tracked open items
Draft build and review cycle | Days 6 to 12 | Sections drafted, consultant integrated, QA performed, and pink/red-style reviews completed | Read-aloud QA, narrative control, and recurring working sessions
Executive review and submission | Days 13 to 20 | Executive review package, final files, SharePoint structure, and compliant submission ready | Readiness checks, clear folder structure, and planned handoff coverage
Finalist rounds 1 and 2 | Post-submission | Speaker notes, slide messaging, likely questions, and live strategy alignment completed | Tampa war room, action plans, and repeated coordination under short notice
Cadence peaked at twice daily with senior leaders, while AI and automation accelerated planning, compliance extraction, and draft production inside a candidate-led process.
Automated planning and recurring governance made a short public-sector timeline executable.

## Slide 7: Results
I measured the impact through finalist progression, reuse, draft speed, and executive review effort rather than through final award visibility.
Metric | Baseline | Result | How Measured
Finalist progression | No assured advancement from an unprepared start | The bid reached 2 finalist presentations | Invitation to two finalist rounds
Reusable bid base | Each school bid rebuilt structure and messaging | About 12 later RNA school bids reused Detroit assets, with about 6 active at once immediately afterward | Observed live reuse across later school-bid production
First-draft speed | About 4 hours to reach a first compliant draft | An about 80% draft could be reached in roughly 5 minutes before tailoring | Compared live prep effort on later similar school bids
Executive review burden | Leaders saw unfamiliar structure and needed repeated writing review | Later bids usually needed only 1 executive review focused on solution and pricing differences | Observed post-Detroit review pattern with executives and pricing
Later school bids shifted toward about 3 hours of pricing and solutioning meetings plus light administrative completion rather than rebuilding the narrative base.
Final award result is unknown, so the claim is anchored in finalist progression, reuse, speed, review effort, and Ann-corroborated turnaround patterns.
Even without final award visibility, the pursuit produced measurable reuse, speed, credibility, and submission outcomes.

## Slide 8: CPD Plan for the Next 24 Months
My next 24 months of development are focused on deepening capture capability, formalizing AI-enabled proposal delivery, and contributing more visibly to the profession.
Timing | Activity | Why It Matters
March to April 2026 | Finish and live-smoke-test my internally developed capture-to-proposal application | Validate a purpose-built operating system for capture and proposal work
April to May 2026 | Actively build government-capture capability | Expand facilities-services advisory work further upstream in the selling cycle
March to June 2026 | Earn the APMP AI Micro-Certification | Align AI-enabled practice with the official APMP credential
March to September 2026 | Increase involvement in the APMP National Capital Area chapter | Contribute more directly through events, speaking, and board-oriented service
By March 2027 | Stand up a turnkey AI-enabled consulting model and develop toward a BPC 2027 webinar | Demonstrate a practical end-to-end AI operating model for capture and proposal management
The CPD plan is tied directly to service expansion, standards alignment, and visible contribution to the profession.

## Slide 9: CPD Application and Knowledge Sharing
I intend to convert learning into reusable capability for clients and into practical advocacy for the proposal profession.
Learning Area | How I Will Apply It | How I Will Share It
Government capture | Move clients upstream from post-RFP response into earlier capture-stage planning | Publish insight articles on the Boss Key LLC website
AI-enabled proposal operations | Use repo-based conversational AI with human judgment in the loop to accelerate compliant delivery | Share methods with APMP chapter peers and through online presentations
Community leadership | Increase contribution to the NCA APMP chapter through events and speaking | Support chapter events and develop conference-level content
Standards-led innovation | Anchor experimentation in recognized APMP good practice | Translate lessons from the APMP AI Micro-Certification into client delivery and peer discussions
The same principle underpins both my impact story and my development plan: the best proposal leadership leaves behind a stronger system, not just a stronger single submission.
Learning is being converted into reusable client capability and visible contribution to the proposal profession.