## Slide 1
Proposal Professional Impact Paper
Detroit Public Schools/RNA Recompete Bid Rescue and Reuse
Candidate Name: Timothy Semenza APMP Candidate Number: 28366 Timeframe: November 2025 to January 2026
Notes: Target time: 0:45
Open by naming the case plainly: this is a Detroit Public Schools recompete for RNA that I led from November 2025 through January 2026. State that the story is not just about producing one proposal under pressure. It is about rescuing an unprepared high-stakes pursuit and turning it into a reusable operating model for later school bids.
Set expectations for the assessor. Explain that you will move from the starting conditions, to how you led the work, to the measurable results, and then close with how you are building on that impact through CPD.

## Slide 2: Summary of Impact
In 20 working days, I took control of an unprepared $85M Detroit Public Schools recompete, coordinated about 15 stakeholders, reached 2 finalist presentations, and turned the work into reusable RNA school-bid infrastructure.
Category | Evidence
Strategic importance | Incumbent work represented more than 25% of RNA's book of business and expanded from about $14M current scope to an $85M target
Leadership role | I led 100% of coordination and about 60% of drafting across executives, pricing, operations, engineering, account management, and an external consultant
Immediate outcome | Compliant submission completed inside about 20 working days and advanced to 2 finalist presentations
Sustained outcome | Detroit-developed content and templates were reused on about 12 later school bids, including about 6 active at once immediately afterward
A high-risk recompete became a reusable school-bid operating model within one compressed pursuit cycle.
Notes: Target time: 1:45
Use this slide to anchor the whole presentation in a few numbers. In about 20 working days, you took control of an unprepared $85 million recompete, coordinated about 15 stakeholders, advanced to 2 finalist presentations, and then converted the work into reusable RNA school-bid infrastructure.
Do not read the slide word for word. Instead, emphasize the before-and-after shift. The immediate challenge was a high-risk recompete with little preparation and weak process discipline. The lasting impact was that one compressed pursuit cycle produced templates, graphics, messaging, and governance habits that were reused across about 12 later school bids.
Close this slide with the main claim you want them to remember: the most important outcome was not just submission under pressure, but the creation of a repeatable school-bid model from a previously ad hoc process.

## Slide 3: The Situation
RNA encountered a Detroit Public Schools recompete without a clear capture plan, minimal executive involvement in the RFP, and a late external consultant, despite the incumbent work making up over 25% of its business.
Stakeholder Group | Who Was Involved | Why They Mattered
Senior leaders | Victoria Arinze (CRO) Mufid Farha (CEO) Mohammad Mufid (COO) Brant Miller (EVP, Ops) | Set direction, made decisions, and represented RNA in finalist activity
Core delivery team | Timothy Semenza (Senior Prop. Manager) Chris Arlen (Proposal Consultant) | Coordinated the pursuit and drafted the response
Solution contributors | Ann Couzins (Senior Pricing Manager) Cheryl Holley-Stanton (Account Manager) Finance, operations, IT | Supplied pricing, staffing, operational, and engineering inputs needed for a credible response
Proposal governance had to replace missing capture discipline before the team could compete credibly.
Notes: Target time: 2:30
Describe the starting point without sounding accusatory. RNA encountered the recompete for Detroit Public Schools without a real capture plan, with minimal executive engagement in the RFP, and with an external consultant added late. At the same time, the incumbent work represented more than 25 percent of RNA's book of business, so the stakes were unusually high.
Explain why that starting point mattered. The problem was not only that time was short. The real problem was that proposal governance had to be built while the bid was already live. Before the team could compete credibly, someone had to create structure, define roles, establish milestones, and give senior stakeholders a way to engage productively.
End by setting up your leadership role. Your job was to replace missing capture discipline with an executable proposal process, while still moving quickly enough to submit a compliant and persuasive response.

## Slide 4: Stakeholder Engagement and Communication
Direct engagement with senior and additional stakeholders was critical because the organization had limited preparation and I had to lead without formal authority.
Stakeholder Group | How I Engaged Them | Evidence of Leadership
Senior leaders | Frequent working sessions, at peak as much as twice daily, plus live decision and review sessions | I set direction, aligned next actions, and led the live, in-person finalist strategy discussion under pressure
Pricing and solution contributors | Live interviews, pricing and staffing mediation, compliance tracking, and focused review of bid-specific changes | I translated pricing and operational discussion into compliant narrative and kept disputed issues from stalling the bid
Consultant and support team | Shared company context, managed drafting split, and maintained SharePoint submission structure | I remained the single point of coordination while enabling useful support from Chris Arlen
Direct engagement and communication created alignment where authority alone would not.
Notes: Target time: 2:30
Frame this slide around leadership without formal authority. You were not operating as a C-suite executive, but you still had to align senior leaders, the consultant, pricing, operations, IT, and site-level expertise around one coherent response. That required a communication style that was concise, practical, and adapted to how each stakeholder actually worked.
Call out the key communication methods. You assigned work verbally in live calls so non-proposal stakeholders could absorb it quickly. You followed that with structured tracking through the compliance matrix and meeting summaries. When written input was vague or unhelpful, you switched to short calls, interviewed the stakeholder directly, and translated their expertise into usable proposal language.
Use one concrete example. Ann Couzins saw you mediate between pricing and leadership so staffing assumptions, pricing rationale, and narrative stayed aligned. That mattered because unresolved disagreement in that area would have delayed the bid and weakened the solution story.
Close by making the principle explicit: direct engagement and communication created alignment where formal authority alone would not.

## Slide 5: Tasks
I stabilized the pursuit through five leadership tasks that gave the team structure, accountability, and decision discipline.
Task | Why It Was Necessary | Main Stakeholders Impacted
Establish bid governance and schedule | No usable capture plan or agreed review cadence existed at release | All senior stakeholders and the external consultant
Develop evaluator and win-theme strategy | The team needed a customer-centered strategy instead of an internally driven narrative | RNA executives, Account Management, and presentation speakers
Elicit and structure SME input | Live operational knowledge had to be turned into compliant proposal content | Pricing, operations, engineering, and Account Management
Draft and quality-control content | The written response and finalist materials had to stay aligned and submission-ready | Consultant, executives, reviewers, and evaluators
Lead review and submission readiness | Readiness could not be left to last-minute judgment | Executive reviewers, consultant, and submission support
Clear task ownership turned a fragmented effort into a manageable response.
Notes: Target time: 2:15
Introduce the five tasks as the leadership framework that stabilized the pursuit. Say that you do not want the assessor to think of this as a general scramble. It became manageable because you defined a small number of clear responsibilities and carried them consistently through the bid.
Walk through the tasks at a high level. First, establish bid governance and the schedule. Second, develop evaluator and win-theme strategy. Third, elicit and structure SME input. Fourth, draft and quality-control proposal and presentation content. Fifth, lead review and submission readiness.
For each task, emphasize why it was necessary. Governance replaced missing capture structure. Evaluator strategy prevented the team from writing inward-looking content. SME elicitation turned operational knowledge into proposal evidence. Drafting and QA kept the written proposal and finalist materials aligned. Review and submission readiness ensured the work could still move forward even if you became unavailable.
Transition to the next slide by saying that the activities show how those tasks operated across the 20-working-day window.

## Slide 6: Activities
I used a milestone-led operating cadence to keep the pursuit on track from RFP receipt through two finalist rounds.
Checkpoint | Approx Timing | What Had To Be Complete | How I Controlled It
RFP receipt and planning | Day 1 | Automated schedule, project plan, and working cadence issued | Power Automate schedule logic and immediate visibility of milestones
Kickoff and evaluator strategy | Days 1 to 2 | Leadership aligned on approach, evaluator research framed, responsibilities assigned | Live kickoff plus customer-focused positioning before drafting expanded
Compliance matrix and SME baseline | Days 2 to 5 | Compliance matrix built and core pricing, operations, and account insight captured | Interviews, Teams follow-up, and tracked open items
Draft build and review cycle | Days 6 to 12 | Sections drafted, consultant integrated, QA performed, and pink/red-style reviews completed | Read-aloud QA, narrative control, and recurring working sessions
Executive review and submission | Days 13 to 20 | Executive review package, final files, SharePoint structure, and compliant submission ready | Readiness checks, clear folder structure, and planned handoff coverage
Finalist rounds 1 and 2 | Post-submission | Speaker notes, slide messaging, likely questions, and live strategy alignment completed | Tampa war room, action plans, and repeated coordination under short notice
Cadence peaked at twice daily with senior leaders, while AI and automation accelerated planning, compliance extraction, and draft production inside a candidate-led process.
Automated planning and recurring governance made a short public-sector timeline executable.
Notes: Target time: 3:15
Treat this slide as a timeline, not as a table to be read row by row. Start with the first checkpoint: as soon as the RFP arrived, you used your Power Automate workflow to generate an initial schedule tied to Shipley-style review milestones. That let you publish an executable plan quickly instead of losing time to manual calendar building.
Next, explain the early operating cadence. You built the compliance matrix, researched the evaluation board, and entered kickoff already oriented around the customer rather than around internal opinion. From there, the cadence became highly active, at times twice daily with senior leaders, plus recurring calls with SMEs such as Cheryl and with Chris Arlin to develop content.
Then cover the middle of the timeline. You used AI and automation to accelerate compliance extraction, draft assembly, and transcript-based content development, but the decisions, quality control, and stakeholder management remained yours. You manually refined the narrative, used read-aloud QA in Word, and kept everyone aligned through recurring meetings and visible tracking.
Finish with the final checkpoints. You organized the SharePoint submission structure so the bid could still be submitted cleanly if you were out, and you carried the written narrative through to two finalist rounds by preparing slides, speaker notes, likely questions, and message discipline. The headline here is that recurring governance made a short public-sector timeline executable.

## Slide 7: Results
I measured the impact through finalist progression, reuse, draft speed, and executive review effort rather than through final award visibility.
Metric | Baseline | Result | How Measured
Finalist progression | No assured advancement from an unprepared start | The bid reached 2 finalist presentations | Invitation to two finalist rounds
Reusable bid base | Each school bid rebuilt structure and messaging | About 12 later RNA school bids reused Detroit assets, with about 6 active at once immediately afterward | Observed live reuse across later school-bid production
First-draft speed | About 4 hours to reach a first compliant draft | An about 80% draft could be reached in roughly 5 minutes before tailoring | Compared live prep effort on later similar school bids
Executive review burden | Leaders saw unfamiliar structure and needed repeated writing review | Later bids usually needed only 1 executive review focused on solution and pricing differences | Observed post-Detroit review pattern with executives and pricing
Later school bids shifted toward about 3 hours of pricing and solutioning meetings plus light administrative completion rather than rebuilding the narrative base.
Final award result is unknown, so the claim is anchored in finalist progression, reuse, speed, review effort, and Ann-corroborated turnaround patterns.
Even without final award visibility, the pursuit produced measurable reuse, speed, credibility, and submission outcomes.
Notes: Target time: 3:30
Lead with the measurement logic. Because you do not know the final award result, you are measuring impact through progression, reuse, speed, and review effort. That is a more defensible claim set than speculating about award outcome.
Walk through the results in order. First, the pursuit advanced to 2 finalist presentations despite starting from an unprepared position. Second, the Detroit work product became a reusable base for about 12 later RNA school bids, including about 6 that were active at once in the immediate aftermath. Third, the time to reach an about 80 percent first compliant draft dropped from roughly 4 hours to roughly 5 minutes when a later Michigan school bid matched the reusable pattern.
Then explain the organizational effect behind those numbers. Later bids often required only one executive review because the messaging and structure had become familiar and trusted. Your effort shifted from rebuilding standard narrative to validating compliance, adapting pricing and staffing discussions into tailored content, and completing the remaining forms and signatures.
Close with the strongest before-and-after statement in the deck. Before Detroit, the school-bid process was ad hoc, low-trust, and review-heavy. After Detroit, it was more standardized, faster to launch, easier for executives to review, and strong enough to support repeated use even without direct award visibility.

## Slide 8: CPD Plan for the Next 24 Months
My next 24 months of development are focused on deepening capture capability, formalizing AI-enabled proposal delivery, and contributing more visibly to the profession.
Timing | Activity | Why It Matters
March to April 2026 | Finish and live-smoke-test my internally developed capture-to-proposal application | Validate a purpose-built operating system for capture and proposal work
April to May 2026 | Actively build government-capture capability | Expand facilities-services advisory work further upstream in the selling cycle
March to June 2026 | Earn the APMP AI Micro-Certification | Align AI-enabled practice with the official APMP credential
March to September 2026 | Increase involvement in the APMP National Capital Area chapter | Contribute more directly through events, speaking, and board-oriented service
By March 2027 | Stand up a turnkey AI-enabled consulting model and develop toward a BPC 2027 webinar | Demonstrate a practical end-to-end AI operating model for capture and proposal management
The CPD plan is tied directly to service expansion, standards alignment, and visible contribution to the profession.
Notes: Target time: 2:00
Explain that your CPD plan is deliberately tied to the same themes as the impact story: stronger upstream capture, stronger operating systems, and stronger contribution to the profession. This is not a generic training list. It is a plan to deepen the areas that most directly affect how you lead proposal work.
Mention the five development priorities briefly. You plan to deepen government capture capability, complete and test your internally developed capture-to-proposal app, stand up a more AI-enabled consulting delivery model, become more active in the APMP National Capital Area chapter, and complete the APMP AI Micro-Certification.
For each one, keep the emphasis on application and sharing. You are not collecting credentials for their own sake. You are building methods you can use with clients, publish through thought leadership, and bring back to APMP peers through chapter activity and conference-level speaking.

## Slide 9: CPD Application and Knowledge Sharing
I intend to convert learning into reusable capability for clients and into practical advocacy for the proposal profession.
Learning Area | How I Will Apply It | How I Will Share It
Government capture | Move clients upstream from post-RFP response into earlier capture-stage planning | Publish insight articles on the Boss Key LLC website
AI-enabled proposal operations | Use repo-based conversational AI with human judgment in the loop to accelerate compliant delivery | Share methods with APMP chapter peers and through online presentations
Community leadership | Increase contribution to the NCA APMP chapter through events and speaking | Support chapter events and develop conference-level content
Standards-led innovation | Anchor experimentation in recognized APMP good practice | Translate lessons from the APMP AI Micro-Certification into client delivery and peer discussions
The same principle underpins both my impact story and my development plan: the best proposal leadership leaves behind a stronger system, not just a stronger single submission.
Learning is being converted into reusable client capability and visible contribution to the proposal profession.
Notes: Target time: 1:30
Use the closing slide to connect the development plan back to the impact story. The same standard applies in both places: good proposal leadership should leave behind a stronger system, not just a stronger single submission.
Explain how learning will be applied. Capture learning will expand your client support upstream. AI and workflow learning will become reusable delivery capability in your consulting practice. Chapter and conference contribution will turn that learning outward so other professionals can adopt what works in their own environments.
Finish with a concise close. The Detroit case showed that you can impose structure, create trust, and leave behind reusable capability under pressure. Your CPD plan is designed to extend that same kind of impact across future clients and across the wider proposal profession.