## Slide 1
Proposal Professional Impact Paper
Detroit Public Schools/RNA Recompete Bid Rescue and Reuse
Candidate Name: Timothy Semenza APMP Candidate Number: 28366 Timeframe: November 2025 to January 2026
Notes: Target time: 0:45
Today I am presenting a Detroit Public Schools recompete that I led for RNA between November 2025 and January 2026. I selected this example because it shows not only how I managed a high-pressure pursuit, but how I turned that pursuit into something reusable for the business afterward.
My presentation will move through four points. First, I will explain the starting conditions and why the bid was high risk. Second, I will show how I led the team and structured the work. Third, I will show the measurable results that came out of the pursuit. Finally, I will explain how my current development plan builds directly on that impact.

## Slide 2: Summary of Impact
In 20 working days, I took control of an unprepared $85M Detroit Public Schools recompete, coordinated about 15 stakeholders, reached 2 finalist presentations, and turned the work into reusable RNA school-bid infrastructure.
Category | Evidence
Strategic importance | Incumbent work represented more than 25% of RNA's book of business and expanded from about $14M current scope to an $85M target
Leadership role | I led 100% of coordination and about 60% of drafting across executives, pricing, operations, engineering, account management, and an external consultant
Immediate outcome | Compliant submission completed inside about 20 working days and advanced to 2 finalist presentations
Sustained outcome | Detroit-developed content and templates were reused on about 12 later school bids, including about 6 active at once immediately afterward
A high-risk recompete became a reusable school-bid operating model within one compressed pursuit cycle.
Notes: Target time: 1:45
In roughly 20 working days, I took control of an unprepared 85 million dollar Detroit Public Schools recompete, coordinated about 15 stakeholders, reached 2 finalist presentations, and converted the work into reusable RNA school-bid infrastructure.
The point I want to emphasize here is the before-and-after change. At the beginning, this was a high-stakes pursuit with very little usable preparation, weak process discipline, and a great deal of dependence on a small number of people. By the end of the pursuit, we had not only submitted a credible bid and advanced to finalist presentations, but had also created reusable templates, graphics, narrative structure, and governance habits that were then used across later school bids.
So the impact was larger than one submission. The more meaningful outcome was that a reactive and inconsistent approach became a repeatable operating model for later RNA school-bid work.

## Slide 3: The Situation
RNA encountered a Detroit Public Schools recompete without a clear capture plan, minimal executive involvement in the RFP, and a late external consultant, despite the incumbent work making up over 25% of its business.
Stakeholder Group | Who Was Involved | Why They Mattered
Senior leaders | Victoria Arinze (CRO) Mufid Farha (CEO) Mohammad Mufid (COO) Brant Miller (EVP, Ops) | Set direction, made decisions, and represented RNA in finalist activity
Core delivery team | Timothy Semenza (Senior Prop. Manager) Chris Arlen (Proposal Consultant) | Coordinated the pursuit and drafted the response
Solution contributors | Ann Couzins (Senior Pricing Manager) Cheryl Holley-Stanton (Account Manager) Finance, operations, IT | Supplied pricing, staffing, operational, and engineering inputs needed for a credible response
Proposal governance had to replace missing capture discipline before the team could compete credibly.
Notes: Target time: 2:30
The starting situation was difficult for three reasons. First, RNA entered the Detroit Public Schools recompete without a meaningful capture plan, even though this was incumbent work and the opportunity was too important to treat casually. Second, senior leaders had not engaged deeply enough with the RFP at the point the bid became active. Third, an external proposal consultant was added late, which meant we were still defining roles and working relationships while the pursuit was already underway.
The stakes were also unusually high. This incumbent work represented more than 25 percent of RNA's book of business, and the company wanted not just to defend the existing work but to make a much larger play. So this was not a routine production bid. It was a visible, time-compressed pursuit with material business significance.
Because of that, the central challenge was not simply writing fast. The real challenge was creating proposal governance while the proposal was already live. Before the team could compete credibly, someone had to establish structure, define responsibilities, create milestones, and give senior stakeholders a way to contribute productively. That became my leadership role in the pursuit.

## Slide 4: Stakeholder Engagement and Communication
Direct engagement with senior and additional stakeholders was critical because the organization had limited preparation and I had to lead without formal authority.
Stakeholder Group | How I Engaged Them | Evidence of Leadership
Senior leaders | Frequent working sessions, at peak as much as twice daily, plus live decision and review sessions | I set direction, aligned next actions, and led the live, in-person finalist strategy discussion under pressure
Pricing and solution contributors | Live interviews, pricing and staffing mediation, compliance tracking, and focused review of bid-specific changes | I translated pricing and operational discussion into compliant narrative and kept disputed issues from stalling the bid
Consultant and support team | Shared company context, managed drafting split, and maintained SharePoint submission structure | I remained the single point of coordination while enabling useful support from Chris Arlen
Direct engagement and communication created alignment where authority alone would not.
Notes: Target time: 2:30
This slide is really about leadership without formal authority. I was not leading from the C-suite, but I still had to align senior executives, the consultant, pricing, operations, IT, and site-level subject matter expertise around one coherent response.
To do that, I adapted my communication style to the people involved. I assigned work verbally during live calls because that was the fastest and most effective way to get engagement from senior stakeholders who were not proposal specialists. I then translated those decisions into structure through meeting summaries, action tracking, and a compliance matrix so the work remained visible and controlled.
When written input was vague, incomplete, or overly generic, I did not allow the process to stall. I moved people into short calls, interviewed them directly, and translated what they knew into usable proposal language. That was especially important with operational stakeholders whose expertise was strong, but whose input did not naturally arrive in proposal-ready form.
One example of that was the pricing and staffing coordination that Ann Couzins directly observed. I often had to bridge the gap between what pricing needed, what leadership meant, and what the proposal narrative needed to say. By doing that in real time, I kept pricing assumptions, staffing rationale, and written messaging aligned. In practice, that communication discipline was one of the reasons the bid kept moving.

## Slide 5: Tasks
I stabilized the pursuit through five leadership tasks that gave the team structure, accountability, and decision discipline.
Task | Why It Was Necessary | Main Stakeholders Impacted
Establish bid governance and schedule | No usable capture plan or agreed review cadence existed at release | All senior stakeholders and the external consultant
Develop evaluator and win-theme strategy | The team needed a customer-centered strategy instead of an internally driven narrative | RNA executives, Account Management, and presentation speakers
Elicit and structure SME input | Live operational knowledge had to be turned into compliant proposal content | Pricing, operations, engineering, and Account Management
Draft and quality-control content | The written response and finalist materials had to stay aligned and submission-ready | Consultant, executives, reviewers, and evaluators
Lead review and submission readiness | Readiness could not be left to last-minute judgment | Executive reviewers, consultant, and submission support
Clear task ownership turned a fragmented effort into a manageable response.
Notes: Target time: 2:15
I stabilized the pursuit through five main tasks. The first was to establish bid governance and the schedule. The second was to develop evaluator and win-theme strategy. The third was to elicit and structure subject matter expert input. The fourth was to draft and quality-control both the proposal and the finalist presentation content. The fifth was to lead review and submission readiness.
I think it is important to show the work in this way because it makes clear that this was not just a scramble that happened to succeed. It became manageable because I translated a chaotic situation into a small number of consistent leadership responsibilities.
Each task served a specific purpose. Governance replaced missing capture structure. Evaluator strategy kept the response focused on the customer rather than on internal opinion. SME elicitation turned operational knowledge into evidence. Drafting and quality control kept the written proposal and later presentation materials aligned. Review and submission readiness made sure the bid could still move forward even if something went wrong at the end.
The next slide shows how those tasks played out across the actual timeline of the pursuit.

## Slide 6: Activities
I used a milestone-led operating cadence to keep the pursuit on track from RFP receipt through two finalist rounds.
Cadence peaked at twice daily with senior leaders, while AI and automation accelerated planning, compliance extraction, and draft production inside a candidate-led process.
Automated planning and recurring governance made a short public-sector timeline executable.
Day 1
Plan
- Auto-build schedule
- Issue project plan
- Set review cadence
Days 1-5
Align
- Kickoff around customer
- Research evaluators
- Build compliance matrix
Days 6-12
Build
- Draft sections
- Integrate consultant
- Run QA and reviews
Days 13-20
Submit
- Package final files
- Align executives
- Protect handoff and submit
Post-submission
Present
- Prepare slide story
- Draft Q&A and notes
- Support 2 finalist rounds
Five operating checkpoints replaced a dense activity table and show how governance moved from planning to finalist delivery.
Notes: Target time: 3:15
I have simplified the activities into five checkpoints because that is the clearest way to show how the bid actually moved.
The first checkpoint was plan. As soon as the RFP arrived, I used my Power Automate workflow to generate an initial schedule tied to review milestones. That let me produce a project plan quickly and establish cadence immediately rather than losing time to manual planning.
The second checkpoint was align. Early in the bid, I built the compliance matrix, researched the evaluation board, and entered kickoff already focused on the customer and the evaluators rather than letting the response become purely internally driven. That gave the team a shared frame for how we would position the bid.
The third checkpoint was build. This is where the drafting, consultant integration, and quality control accelerated. I used AI and automation to speed compliance extraction, transcript-based drafting, and early content assembly, but I remained responsible for the judgment, the message control, and the quality. I also used read-aloud quality checks in Word and recurring working sessions to keep the proposal coherent.
The fourth checkpoint was submit. I aligned executives for review, packaged the final files, and organized the SharePoint structure so the bid could still be submitted cleanly even if I became unavailable. That mattered because I did in fact become sick at the end of the cycle, and the structure I put in place allowed the handoff to work.
The fifth checkpoint was present. After submission, I carried the written narrative through into the finalist rounds by preparing slide messaging, speaker notes, likely questions, and response guidance. So the overall point of this slide is that recurring governance made a very short public-sector timeline executable.

## Slide 7: Results
I measured the impact through finalist progression, reuse, draft speed, and executive review effort rather than through final award visibility.
Even without final award visibility, the pursuit produced measurable reuse, speed, credibility, and submission outcomes.
Finalist progression
Baseline
No assured advancement from an unprepared start
Result
Reached 2 finalist presentations
Measured by
Invitations to 2 finalist rounds
Reusable bid base
Baseline
Each school bid rebuilt structure and messaging
Result
About 12 later RNA school bids reused Detroit assets, with about 6 active at once
Measured by
Observed live reuse across later school-bid production
First-draft speed
Baseline
About 4 hours to reach a first compliant draft
Result
An about 80% draft could be reached in roughly 5 minutes before tailoring
Measured by
Compared live prep effort on later similar bids
Executive review burden
Baseline
Repeated review of unfamiliar writing and structure
Result
Later bids usually needed 1 executive review focused on solution and pricing differences
Measured by
Observed post-Detroit review pattern with executives and pricing
Notes: Target time: 3:30
I want to be careful here and stay within claims I can defend. I do not know the final award result, so I am not presenting impact in terms of a win claim. Instead, I am measuring the outcome through finalist progression, reuse, speed, and review effort.
First, the pursuit reached 2 finalist presentations. Given the starting point, that was a meaningful result because there was no assured advancement when the bid began.
Second, the Detroit work became a reusable base for later RNA school bids. About 12 later bids reused the assets that came out of this pursuit, and about 6 of those were active at one time in the immediate aftermath. That meant the Detroit effort did not end as a one-time response. It became the foundation for subsequent production.
Third, the time to reach an approximately 80 percent first compliant draft changed dramatically on later similar bids. Before Detroit, that work could take about 4 hours. After Detroit, when the bid pattern matched what we had already built, I could get to that draft state in about 5 minutes before tailoring.
Fourth, the executive review burden became lighter. Later bids usually needed only one executive review focused on pricing or solution differences, rather than repeated review of unfamiliar writing and structure. In other words, leadership became more comfortable because the messaging and format had become more standardized and more trusted.
So the strongest before-and-after statement I can make is this: before Detroit, RNA's school-bid process was ad hoc, low-trust, and review-heavy. After Detroit, it was more standardized, faster to launch, easier to review, and strong enough to support repeated reuse.

## Slide 8: CPD Plan for the Next 24 Months
My next 24 months of development are focused on deepening capture capability, formalizing AI-enabled proposal delivery, and contributing more visibly to the profession.
Timing | Activity | Why It Matters
March to April 2026 | Finish and live-smoke-test my internally developed capture-to-proposal application | Validate a purpose-built operating system for capture and proposal work
April to May 2026 | Actively build government-capture capability | Expand facilities-services advisory work further upstream in the selling cycle
March to June 2026 | Earn the APMP AI Micro-Certification | Align AI-enabled practice with the official APMP credential
March to September 2026 | Increase involvement in the APMP National Capital Area chapter | Contribute more directly through events, speaking, and board-oriented service
By March 2027 | Stand up a turnkey AI-enabled consulting model and develop toward a BPC 2027 webinar | Demonstrate a practical end-to-end AI operating model for capture and proposal management
The CPD plan is tied directly to service expansion, standards alignment, and visible contribution to the profession.
Notes: Target time: 2:00
My CPD plan is intentionally tied to the same themes as this impact story. I want to deepen my ability to work further upstream in capture, build stronger operating systems for proposal delivery, and contribute more visibly to the profession.
Over the next 24 months, I plan to deepen my government capture capability, complete and test my internally developed capture-to-proposal application, formalize a more AI-enabled consulting delivery model, become more active in the APMP National Capital Area chapter, and complete the APMP AI Micro-Certification.
I do not view those as separate activities. Together, they reflect how I want to grow as a proposal leader. I want to be stronger at identifying opportunity earlier, stronger at creating repeatable systems around the work, and stronger at sharing what I learn in ways that are useful to other practitioners.

## Slide 9: CPD Application and Knowledge Sharing
I intend to convert learning into reusable capability for clients and into practical advocacy for the proposal profession.
Learning Area | How I Will Apply It | How I Will Share It
Government capture | Move clients upstream from post-RFP response into earlier capture-stage planning | Publish insight articles on the Boss Key LLC website
AI-enabled proposal operations | Use repo-based conversational AI with human judgment in the loop to accelerate compliant delivery | Share methods with APMP chapter peers and through online presentations
Community leadership | Increase contribution to the NCA APMP chapter through events and speaking | Support chapter events and develop conference-level content
Standards-led innovation | Anchor experimentation in recognized APMP good practice | Translate lessons from the APMP AI Micro-Certification into client delivery and peer discussions
The same principle underpins both my impact story and my development plan: the best proposal leadership leaves behind a stronger system, not just a stronger single submission.
Learning is being converted into reusable client capability and visible contribution to the proposal profession.
Notes: Target time: 1:30
The closing point is that I want my development to work the same way this impact story worked. I do not want learning to stay personal or theoretical. I want it to become reusable capability.
Capture learning will allow me to support clients further upstream. AI and workflow learning will become practical delivery capability in my consulting work. Chapter participation, thought leadership, and conference speaking will help me turn those lessons outward so other proposal professionals can apply them in their own environments.
So the same principle connects both halves of this presentation. In the Detroit case, I helped turn one pressured pursuit into a stronger system for later work. In my CPD plan, I am trying to do the same thing with my own development by turning learning into repeatable value for clients and for the profession.